## Project Items
Author | Edited By | Last Edited | Type | Title | # | State | Repository | Assignees | Labels | Milestone | Body | Comments (#) | Comments | Reviews | Linked PRs / Issues | Created | Updated | URL | Status
bjach04 |  |  | Issue | Post new volunteer or internship opportunities | 2 | CLOSED | drew-csci/opportunity_app_srping_2026 | devhirpara29 | High Priority |  | As an organization user, I want to create and publish new volunteer or internship opportunities by providing detailed information such as the role description, required skills, location, duration, and application deadline, so that qualified volunteers can understand the role. Acceptance Criteria: Given I am logged in as a organization user When I navigate to the dashboard Then I can see an option to “Post New Opportunity” Implementation: Implement “Post new opportunity” access in the Organization dashboard Build/design UI and functions for opportunity creation form. Build confirmation and listing update. Story Points: 5 | 0 |  |  |  | 2026-02-25 | 2026-05-11 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/2 | Ready
mjuliano328 | mjuliano328 | 2026-04-18 | Issue | US-018 - Browse opportunties by cause area (2 story points) | 74 | OPEN | drew-csci/opportunity_app_srping_2026 | nakiwem | Low Priority |  | User Story: As a volunteer, I want to browse opportunities grouped by cause area (Environment, Education, Health, Animals, etc.) so that I can explore interests even when I don't have a specific keyword in mind. Acceptance Criteria: - [ ] A "Browse by Cause" section is available from the search page or dashboard. - [ ] Each cause area displays an icon, short description, and count of active opportunities. - [ ] Clicking a cause area opens the search page with that cause pre-filtered. - [ ] At minimum the following cause areas are supported: Environment, Education, Health, Animals, Advocacy, Arts. Tasks: - [ ] Define cause-area taxonomy and add a cause_area field to the opportunity schema. - [ ] Build a Browse by Cause grid component on the search/landing page. - [ ] Wire cause selection to the existing search filter state. Wireframe Mapping: Opportunity Search & Browse (Wireframe 3). | 0 |  |  |  | 2026-04-18 | 2026-04-22 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/74 | Backlog
mjuliano328 |  |  | Issue | US-034 - Verify email address on account creation (3 story points) | 90 | OPEN | drew-csci/opportunity_app_srping_2026 | bjach04 | High Priority |  | User Story: As the platform, I need newly registered users to verify their email address so that the account is genuinely reachable and the notification features (US-003, US-014) actually work. Acceptance Criteria: - [ ] On successful signup, the user receives a verification email with a signed, 24-hour-valid link. - [ ] Until verified, the account can log in but a persistent banner displays "Please verify your email" with a [Resend] button. - [ ] Clicking the verification link marks the account verified and removes the banner. - [ ] Unverified accounts cannot post opportunities (organizations) or submit applications (volunteers). - [ ] Verification links expire after 24 hours; expired links prompt the user to request a new one. Tasks: - [ ] Add email_verified_at column and verification_token table to user schema. - [ ] Build the verification email template and sender. - [ ] Build the verification landing page that consumes the token. - [ ] Guard gated actions (post opportunity, apply) behind the verified flag. Wireframe Mapping: Welcome &amp; Login (Wireframe 1). | 0 |  |  |  | 2026-04-18 | 2026-04-27 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/90 | In Progress
mjuliano328 |  |  | Issue | US-020 - Edit or close an existing opportunity posting (3 story points) | 76 | OPEN | drew-csci/opportunity_app_srping_2026 | mjuliano328 | High Priority |  | User Story: As an organization, I want to edit details of a posted opportunity or close it once the role is filled so that the information students see is accurate. Acceptance Criteria: - [ ] Each of the organization's posted opportunities has [Edit] and [Close] controls visible to the organization only. - [ ] Editing an opportunity updates it in place; the edit is visible to all viewers within 60 seconds. - [ ] Closing an opportunity hides it from search results but keeps it visible on the org's profile in a "Past Opportunities" section. - [ ] Already-submitted applications remain accessible after closing. - [ ] A confirmation dialog appears before closing, warning the organization that the action cannot be undone by them (only by an admin). Tasks: - [ ] Add an edit opportunity form (reuse the Post an Opportunity layout). - [ ] Implement close-opportunity action that toggles opportunity status and archives from search index. - [ ] Add Past Opportunities section to organization profile view. Wireframe Mapping: Post an Opportunity (Wireframe 7); Organization Profile (Wireframe 5). | 0 |  |  |  | 2026-04-18 | 2026-04-22 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/76 | In Review
devhirpara29 |  |  | Issue | Volunteer Dashboard | 15 | CLOSED | drew-csci/opportunity_app_srping_2026 | bjach04 | High Priority |  | As a student volunteer, I want a personalized home dashboard that shows recommended volunteer opportunities and quick actions so that I can easily find opportunities that match my interests and quickly manage my application, profile and experiences from one place. Acceptance Criteria:- 1)The dashboard shows recommended volunteer opportunities 2) I can quickly access my applications, profile and experience section 3) The dashboard should feel simple and helpful not cluttered Implementation Task:- (Story Points-5) 1)Create a student home dashboard page. 2)Add a recommended opportunity section with an Apply button. 3) Add a quick access button for Applications, profile and experience. Wireframe:- Student Home Dashboard | 0 |  |  |  | 2026-03-01 | 2026-03-26 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/15 | Done
bjach04 |  |  | Issue | Redesign Home Page for Cleaner UI | 109 | CLOSED | drew-csci/opportunity_app_srping_2026 | bjach04 | enhancement |  | The home page UI needs to be redesigned to provide a cleaner and more visually appealing user experience. Improve layout, spacing, typography, and overall organization to create a more modern and user-friendly appearance. **Goals:** - Simplify and declutter the home page - Ensure consistent spacing and alignment - Improve color scheme and font choices - Make important features and information easy to find - Align with current UI/UX best practices **Acceptance Criteria:** - Updated home page design is implemented - Visual consistency across different screen sizes - No loss of core features or information story points: 3 | 0 |  |  |  | 2026-05-12 | 2026-05-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/109 | Done
bjach04 |  |  | Issue | Search and filter volunteer/internship opportunities | 1 | CLOSED | drew-csci/opportunity_app_srping_2026 | bjach04 | High Priority |  | As a volunteer, I want to be able to search and filter volunteer and internship opportunities using keywords that apply the filters (such as location, cause, duration, skills) so that I can quickly find positions that would match my interests. Acceptance criteria: Given I am on the opportunities page. When I enter a keyword in the search bar. Then the system displays opportunities that match the keyword. Implementation: Build/Design the search input/handling Implement the filtering method Display the filtered result Story Points: 3 | 0 |  |  |  | 2026-02-25 | 2026-05-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/1 | Done
bjach04 |  |  | Issue | Add Log In / Sign Up with Google | 111 | CLOSED | drew-csci/opportunity_app_srping_2026 | bjach04 |  |  | **Summary:** Implement the ability for users to log in and sign up using their Google accounts. This feature should be available on both the login and sign up pages, providing a seamless and secure authentication option in addition to existing methods. **Acceptance Criteria:** - Users can log in using their Google accounts from the login page. - Users can register/sign up with their Google accounts from the sign up page. - Google sign-in/signup buttons are clearly labeled and distinguished from regular login/sign up methods. - On successful Google authentication, user data is appropriately handled/stored in accordance with app requirements. - Proper error handling for failed, cancelled, or denied authentication attempts. - Relevant instructions/tooltips for users are provided if necessary. **Additional Notes:** - Ensure compliance with Google's OAuth and API guidelines. - Update documentation and user guides as needed. Story Points: 5 | 0 |  |  |  | 2026-05-12 | 2026-05-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/111 | Done
nakiwem | nakiwem | 2026-03-04 | Issue | Create and manage organization profile with impact metrics | 40 | CLOSED | drew-csci/opportunity_app_srping_2026 | nakiwem | High Priority |  | As an organization, I want to create and manage our organization’s profile with impact metrics so that student volunteers can understand our mission and the difference/change we want to make. Acceptance Criteria: Organization profile saves required information (name, mission, location, contact info) Allows add/edit/delete of impact metrics Saves profile information after logging out Displays profile information after saving Implementation Tasks: Build/Design organization profile UI (name, mission, location, contact info) Implement add/edit/delete functionality for profile Connect impact metrics and organization profile to database Wireframe: Organization Profile (Public View) - (Wireframe 5) Story Points: 5 | 0 |  |  |  | 2026-03-02 | 2026-04-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/40 | Done
nakiwem | nakiwem | 2026-03-04 | Issue | Create and manage volunteer profile with experience history | 41 | CLOSED | drew-csci/opportunity_app_srping_2026 | nakiwem | High Priority |  | As a volunteer (student), I want to create and manage my profile with my experience history so that organizations can view my past volunteer experience and skills so that I can be matched with suitable volunteer opportunities. Acceptance Criteria: Volunteer profile saves required information (name, email, phone) Allows add/edit/delete of experience entries and associated volunteer organizations Displays profile information after saving Saves profile information after logging out Implementation Tasks: Build/Design student profile UI w/ a personal info (name, email, phone) and experience section Implement add/edit/delete functionality for profile Build/Design profile summary view page Wireframe: Student Profile (Public View) - (Wireframe 6) Story Points: 5 | 0 |  |  | PR #50 (MERGED) - Created Volunteer Profile Page - Issue #41 by nakiwem — https://github.com/drew-csci/opportunity_app_srping_2026/pull/50 PR #72 (MERGED) - Midterm dev by devhirpara29 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/72 | 2026-03-02 | 2026-03-30 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/41 | Done
mjuliano328 |  |  | Issue | US-026 - View and manage current active volunteers (3 story points) | 82 | OPEN | drew-csci/opportunity_app_srping_2026 | mjuliano328 | High Priority |  | User Story: As an organization, I want to see a list of volunteers currently active on my opportunities so that I can track who is engaged and mark their participation as completed when appropriate. Acceptance Criteria: - [ ] The Current Volunteers tile on the organization dashboard opens a list of all accepted-status applications. - [ ] Each row shows volunteer name, opportunity title, start date, and current status. - [ ] The organization can click [Mark Completed] to transition a volunteer's participation to completed; this adds the experience to the volunteer's profile automatically (see Section 5.2). - [ ] The list can be filtered by opportunity. Tasks: - [ ] Build Current Volunteers list component reading from accepted-status applications. - [ ] Implement the Mark Completed action that writes a completed experience to the volunteer's profile. - [ ] Add opportunity-based filter control. Wireframe Mapping: Organization Home Dashboard (Wireframe 4). | 0 |  |  |  | 2026-04-18 | 2026-04-30 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/82 | Done
mjuliano328 | mjuliano328 | 2026-03-04 | Issue | US-012: Receive and Respond to Volunteer Inquiries (5 story points) | 31 | OPEN | drew-csci/opportunity_app_srping_2026 | mjuliano328 | Medium Priority |  | User Story: As an organization, I want to access the messages from student volunteers which have been sent to me and respond to them, so that I can be in open communication with those willing to participate in my organization. Acceptance Criteria: - [ ] Organization should be able to open an inbox and see inquiries, sorted by time of sending - [ ] Should have graphic on UI that displays number of unread inquiries in inbox - [ ] Should be able to open individual messages to read them - [ ] Create a “read” receipt (?) - [ ] Text field to write a reply, ability to send message privately to volunteer - [ ] Character limit (?) - [ ] Helpful message for when text field is empty (or character limit is exceeded) Tasks: - [ ] Build UI for inbox page for organizations, including inquiries sorted by date of receipt - [ ] Build popup for when a specific inquiry is clicked, that allows user to read message and has a prompt to reply - [ ] Create text field for a reply, with ability to send | 0 |  |  |  | 2026-03-02 | 2026-04-10 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/31 | Done
NguyenTin2026 |  |  | Issue | US-011 – Send messages to organizations with AI-assisted FAQ responses | 52 | CLOSED | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | Stories Points: 4 User story: As a volunteer, I want to send messages to organizations with AI-assisted FAQ responses so that I can quickly get answers to my questions. Acceptance Criteria: - The volunteer can open the messaging section - The volunteer can select an organization to message - The volunteer can type and send messages - The system provides AI-assisted FAQ suggestions - The organization receives the message - The volunteer can see sent messages in the chat Tasks: - Build/Design messaging UI interface - Implement message sending functionality - Connect messaging system to database - Integrate AI-assisted FAQ response feature - Ensure messages are stored and displayed properly Wireframe Mapping: - Messaging section – Student Dashboard | 0 |  |  | PR #54 (MERGED) - Issue #52: Add organization messaging with AI-assisted FAQ responses by NguyenTin2026 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/54 | 2026-03-25 | 2026-04-08 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/52 | Done
mjuliano328 |  |  | Issue | Build UI for inbox page for organizations, including inquiries sorted by date of receipt | 32 | OPEN | drew-csci/opportunity_app_srping_2026 | mjuliano328 |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-30 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/32 | Done
mjuliano328 | mjuliano328 | 2026-03-04 | Issue | US-010: Post and Share Completed Volunteer Opportunities (3 Story Points) | 35 | OPEN | drew-csci/opportunity_app_srping_2026 | mjuliano328 | Low Priority |  | User Story: As a student, I want to post opportunities which I have completed, so that other users can see what experience I have Acceptance Criteria: - [ ] Can access separate dashboard that contains completed opportunities - [ ] Option to mark opportunity as complete - [ ] Organization can approve or deny that the opportunity is completed - [ ] When approved, create dashboard post that says the opportunity is completed - [ ] When denied, privately notify student of denial Tasks: - [ ] Build UI for completed opportunity dashboard for students/notification of completion for organizations - [ ] Access database to read/mark completed status of opportunity - [ ] Create automatic post on dashboard notifying users of opportunity completion, based on completed status | 0 |  |  | PR #56 (MERGED) - Issue #35: Mark opportunities as completed and create dashboard post for completed opportunities by mjuliano328 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/56 | 2026-03-02 | 2026-03-30 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/35 | Done
nakiwem | nakiwem | 2026-03-04 | Issue | Create apply to opportunity and track application status page | 42 | CLOSED | drew-csci/opportunity_app_srping_2026 | nakiwem | High Priority |  | As a volunteer, I want to be able to apply for opportunities and track the application status so that I know whether I have been accepted, denied, or am still under review. Acceptance Criteria: Allows volunteer to fill out and submit an application for an opportunity Prevents volunteer from sending out duplication applications to organization Volunteer receives a message when their application has been submitted Displays application status (accepted, denied, or still under review) Updates application status when organization has made a decision Volunteer should be able to save their application process and go back later to complete Implementation Tasks: Build/Design application submission form and apply button Implement backend logic to save and store submissions Prevent duplication applications to be submitted for same opportunity Build/Design application tracking view for student volunteer Wireframe: Volunteer Profile (Public View) - (Wireframe 6) & Opportunity Search & Browse (Wireframe 3) Story Points: 5 | 0 |  |  |  | 2026-03-02 | 2026-04-08 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/42 | Done
NguyenTin2026 |  |  | Issue | US-009 – View peer activity feed of recent experiences | 51 | CLOSED | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | Stories Points: 3 User Story: As a volunteer, I want to view a peer activity feed of recent experiences so that I can see what other volunteers have done and learn from their experiences. Acceptance Criteria: - The volunteer can access the activity feed from the dashboard or social section - The system displays recent volunteer experiences from other users - Each activity shows volunteer name, organization, and experience title - The volunteer can scroll through the activity feed - If there are no activities, the system displays a message "No recent activity available" Tasks: - Build/Design activity feed UI page - Connect activity feed to database to retrieve experiences - Display activity information in chronological order - Ensure the page loads properly and allows scrolling Wireframe Mapping: - Student Home Dashboard – Social Feed section | 0 |  |  | PR #53 (MERGED) - Issue #51: Add peer activity feed of recent experiences by NguyenTin2026 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/53 | 2026-03-25 | 2026-04-08 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/51 | Done
modestmag-dev |  |  | Issue | Create the HTML-based login-related forms that check for account information to validate credentials, store information entered in, and allow for password resets to occur (with proper security measures implemented). | 22 | CLOSED | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-04-08 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/22 | Done
mjuliano328 |  |  | Issue | US-035 - Report inappropriate content (2 story points) | 91 | OPEN | drew-csci/opportunity_app_srping_2026 | mjuliano328 | Medium Priority |  | User Story: As a user, I want to report inappropriate content (an opportunity, a message, a profile, or a news update) so that admins can review it and keep the platform safe. Acceptance Criteria: - [ ] A Report control is available on every opportunity, profile, and news-update view. - [ ] Clicking Report opens a short form with a reason dropdown (spam, harassment, misleading, other) and optional free-text notes. - [ ] Submitting the form creates an entry in the admin moderation queue (see US-036). - [ ] The reporting user sees a confirmation that their report was received; their identity is not shown to the reported party. Tasks: - [ ] Design report schema (reporter_id, target_type, target_id, reason, notes, status). - [ ] Build the Report control and modal. - [ ] Create the submission endpoint and queue entry. Wireframe Mapping: Applies across Opportunity detail, Organization Profile (Wireframe 5), Peer Activity Feed (Wireframe 9). | 0 |  |  |  | 2026-04-18 | 2026-04-30 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/91 | Done
bjach04 |  |  | Issue | Follow organizations and subscribe to updates | 4 | CLOSED | drew-csci/opportunity_app_srping_2026 | devhirpara29 | Medium Priority |  | As a volunteer, I want to follow organizations and subscribe to their updates so that I can stay informed about new opportunities, events, and announcements that match my interests. Acceptance Criteria: Given I am logged in as a volunteer When I visit an organization’s profile page Then I can click a “Follow” button to follow the organization Implementation: Implement follow/unfollow functionality Display followed organizations “Organizations I Follow” Implement notification system for updates Manage follow/subscription preferences Story Points: 5 | 0 |  |  | PR #59 (MERGED) - Add follow/unfollow organizations feature by devhirpara29 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/59 PR #62 (MERGED) - Dev hirpara branch 1 by devhirpara29 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/62 PR #72 (MERGED) - Midterm dev by devhirpara29 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/72 | 2026-02-25 | 2026-04-08 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/4 | Done
devhirpara29 | devhirpara29 | 2026-03-01 | Issue | Organization Dashboard | 16 | CLOSED | drew-csci/opportunity_app_srping_2026 | devhirpara29 | High Priority |  | As an organization, I want a home dashboard that gives me an overview of recent applications so that I can quickly review applications, view student details and accept or decline volunteers while easily navigating to my profile, messages and posted opportunities. Acceptance Criteria:- 1. The dashboard shows recent application . 2. I can quickly view applicants details and take action either Accept or Decline. 3. I can easily navigate to my profile, messages and posted opportunities. Implementation Task:- (Story Points- 5) 1. Create a organization home dashboard page 2. Show a recent application list 3. Add accept or decline buttons for each applicant. 4. Add easy navigation to profile, Messages and posted opportunities. Wireframe:- Organization Home Dashboard | 0 |  |  | PR #71 (MERGED) - Merge main into feature/issue-4-follow-organizations - kept follow fe… by devhirpara29 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/71 | 2026-03-01 | 2026-04-04 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/16 | Done
pwei454 |  |  | Issue | US-008 - Send Application Reminder to Organization | 18 | CLOSED | drew-csci/opportunity_app_srping_2026 | pwei454 | Medium Priority |  | US-008 - Send Application Reminder to Organization As a volunteer, I want to send a reminder for my pending application so that the organization may review my application sooner. Priority: Medium Story Points: 3 Acceptance Criteria: 1. The reminder button appears only when application status is "Applied." 2. Volunteers can click "Remind About Me." 3. When the volunteer clicks "Remind About Me," a notification is sent to the organization. 4. The reminder option is not available if application status changes to "Accepted" or "Declined." Implementation Tasks: 1. Add the "Remind About Me" button to pending applications. 2. Implement a backend notification trigger for reminders. 3. Ensure the reminder option disappears when status changes. Wireframe Mapping: Student Home Dashboard – Your Applications (Wireframe 2) | 0 |  |  | PR #100 (MERGED) - Implement US-008 application reminder feature by pwei454 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/100 PR #105 (MERGED) - Fix US-008 reminder status check by pwei454 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/105 | 2026-03-01 | 2026-05-10 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/18 | Done
modestmag-dev | modestmag-dev |  | Issue | Add page redirects to the user’s main homepage upon successfully logging into their account. | 24 | CLOSED | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 1 | [modestmag-dev 2026-04-08] Here, this functionality doesn't REALLY just redirect to the user's main homepage after login, but does something better: it either redirects to a secure page that the user currently requests during login (which is likely the page they are currently logging into that isn't the main page), OR redirects to their own homepage if there is no special page present. |  | PR #65 (MERGED) - Feature/issue 24: Added Homepage Redirect after Login (Based on User Type) by modestmag-dev — https://github.com/drew-csci/opportunity_app_srping_2026/pull/65 | 2026-03-01 | 2026-05-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/24 | Done
modestmag-dev | modestmag-dev |  | Issue | Implement the whole reset password workflow properly, by allowing automated password reset emails to be sent to correct email addresses for the process to progress. | 23 | CLOSED | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 1 | [modestmag-dev 2026-04-08] Note: Whole password reset workflow was implemented previously alongside the forms in one sitting (during midterm project). However, SMTP credentials still need to be established for the emails to actually be sent out. |  |  | 2026-03-01 | 2026-05-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/23 | Done
modestmag-dev |  |  | Issue | Build-up and design generalized UI for the login/create account/reset password workflows. | 20 | CLOSED | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  | PR #68 (MERGED) - Feature/Issue 20: Enhanced UI for the Login Workflow to Reference by modestmag-dev — https://github.com/drew-csci/opportunity_app_srping_2026/pull/68 | 2026-03-01 | 2026-05-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/20 | Done
pwei454 |  |  | Issue | US-007 Review and manage incoming volunteer applications | 17 | CLOSED | drew-csci/opportunity_app_srping_2026 | pwei454 | High Priority |  | As an organization user, I want to review and manage incoming volunteer applications so that I can efficiently select qualified students and manage active volunteers. Priority: High Story Points: 5 Acceptance Criteria: 1. The organization can view a list of incoming applications grouped by opportunity. 2. Each application displays: - Student name - Opportunity title - Date applied - Current status 3. The organization can click “View Profile” to see the student’s profile and experience history. 4. The organization can select “Accept” or “Decline.” 5. When an organization selects “Accept,” status updates to “Accepted.” 6. When an organization selects “Decline,” status updates to “Declined.” 7. Volunteers receive a notification when status changes. 8. Accepted students appear in the “Current Volunteers” list. 9. Status changes persist after page refresh. Implementation Tasks: 1. Build the “Review Volunteers” list view for organizations. 2. Implement backend logic to retrieve applications grouped by opportunity. 3. Add Accept and Decline button functionality. 4. Implement notification trigger when application status changes. Wireframe Mapping: Organization Home Dashboard (Wireframe 4) | 0 |  |  | PR #55 (MERGED) - US-007: #17 build organization dashboard by pwei454 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/55 PR #106 (MERGED) - US-007: add notification trigger, status colors, view profile, and im… by pwei454 — https://github.com/drew-csci/opportunity_app_srping_2026/pull/106 | 2026-03-01 | 2026-04-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/17 | Done
modestmag-dev |  |  | Issue | (Ryan DeVita) Account Registration/Login Management (Estimate: 3 Story Points) | 19 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev | High Priority |  | ### **User Stroy:** As a user of the Opportunity System, I want to be allowed to create/log into an account tied to my specific role (Organization/Volunteer) and later be able to manage the password that is associated with it, so that I can access my personalized data that is linked with my profile (such as any offerings I have set up or specific opportunities I have access to depending on my role), identify myself properly for other users to see, and regain control over my account in the case that I forget my password (or want the ability to reset it for any other reason). ### **Acceptance Criteria:** - After clicking on the login selection of the website, a user is then presented with two buttons that they can click to indicate whether or not they are a Student (or Volunteer) or an Organization User, and upon clicking a button, the user is sent to the login page associated with their role. - Each login page allows the user to input their email and password into two field boxes, with a login button placed below them that allows them to sign into their account. - Extra links below the login box that direct the user to either create a new account (if not set up already) or reset their password are accessible. - When resetting a password, a user can enter their email into a field, which will then send a confirmation link to it if it is validated as the one linked to their account. Clicking on the link lets the user type in a new password and confirm it to change the password successfully. - A button on the original password reset page below the email field, when clicked, returns the user to their respective login page. - On the Create Account flow, a user is prompted to enter their email and initial password, alongside an extra password validation field just in-case. - Upon account creation and login, the user is directed to their home dashboard, where they can manage their personal account information and such. - Each page within the login process can also be confirmed by pressing the enter key alongside pressing the on-screen button. - Buttons and other login elements are located on the center of the screen and evenly spaced, for ease of access. - If the user fails to enter their login details correctly 10 times, they are locked out from logging in for a short 10-minute period. - Users are logged out of their account after 30 minutes of website inactivity. - Pages take under 5 seconds to load-in properly. - SQL injection and cross-site scripting attempts are rejected by the password field for security. - Incorrectly entered/non-existing info returns a mis-match message to the user. ### **Tasks:** - Build-up and design generalized UI for the login/create account/reset password workflows. - Create the HTML-based login-related forms that check for account information to validate it in real-time for existing account logins, store account information for new accounts, and initiate a password reset for an account if requested (each with enter key functionality and injection/scripting security measures). - Implement the whole reset password workflow properly, by allowing automated password reset emails to be sent to correct email addresses for the process to progress. - Add page redirects to the user’s main homepage upon successfully logging into their account. **Wireframe: Welcome & Login (Wireframe 1)** | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/19 | Backlog
modestmag-dev |  |  | Issue | (Ryan DeVita) Notification and Privacy Configuration (Estimate: 4 Story Points) | 25 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev | Medium Priority |  | ### **User Story:** As a user of the Opportunity System, I want to be able to access a settings page for my account that allows for me to toggle notifications and privacy features that are linked to it on and off, so that way I can configure how others see my profile and how I am notified about information to my liking. ### **Acceptance Criteria:** - Within the dropdown menu that appears near a user’s profile area, a ‘Settings’ selection is present which allows users to control their overall experience using the website through privacy, notification, and other important options. - There are multiple sub-tabs within the settings page that allows the user to access hyper-specific settings they are looking for, keeping things relatively organized. - In the ‘Notifications’ sub-tab, there are toggle buttons for both update and general notifications (email for both forms of the service and push for the mobile app exclusively, though can still be toggled on desktop just in-case) that the user can turn on and off at any time. - If enabled, email notifications are sent to the email associated with the user’s account, while push notifications are sent as pop-up notifications (different based on phone’s system preferences) to the device that the app is associated with. Update notifications can be added to the pool based on that toggle’s setting, but matching notifications and messages you have received are included in this pool by default. - In the ‘Privacy’ settings, there is a toggle button that can also be turned on and off at will, which enables or disables whether or not a Volunteer’s completed experiences are publicly visible (a setting exclusive for students specifically). A plethora of other privacy options (such as cookies management options and account history settings) should also be manageable in the same fashion for all accounts. - In the ‘Personalization’ section, a toggle button that enables and disables a dark and light visual theme is present to offer users with simple customization options that help them feel the most comfortable using the system. Other personalization options (such as text size, for instance) can also be toggled through dropdown menu options and the like. - A friendly, simplistic UI is implemented where setting types are listed out on the left side of the page, while togglable options are displayed as simple buttons that change color based on your selected theme. All buttons and dropdown menus are designed to fit the general appearance of this screen as cleanly as possible. ### **Tasks:** - Add a ‘Settings’ listing within the nav portion of each user type’s dashboard, to allow for ease of access to the feature. - Build-up and design the settings page, so that its UI is visually appealing for the user and easy for them to navigate through. - Implement crucial privacy, personalization, and notification settings to optimize the user’s experience as much as possible, making sure they have access to enabling/disabling a variety of features whenever they desire (while also adding the Volunteer specific setting to enable and disable experience completion public listings and making sure it is exclusive to those types of users). - Create an automated notification system that is able to send over notifications of certain types to users based on their specified preferences in that field. **Wireframes: Settings - (Wireframe 10) ALONG WITH Student Home Dashboard - (Wireframe 2) and Organization Dashboard - (Wireframe 4) (Last two wireframes specifically for the first task).** | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/25 | Backlog
mjuliano328 |  |  | Issue | US-033 - Delete own account with confirmation (3 story points) | 89 | OPEN | drew-csci/opportunity_app_srping_2026 | nakiwem | Low Priority |  | User Story: As a user, I want to permanently delete my account and associated personal data so that I can leave the platform cleanly when I no longer need it. Acceptance Criteria: - [ ] Settings > Account has a [Delete Account] action that opens a two-step confirmation modal. - [ ] The modal explains what will be deleted (profile, applications, messages, saved items) and what will be retained in anonymized form (e.g., verified experience records on the org side). - [ ] Confirmation requires typing the word DELETE and entering the current password. - [ ] On success, the user is logged out and all personal identifiers are removed from the database within 24 hours. - [ ] Email receipts confirming deletion are sent to the account email. Tasks: - [ ] Design deletion pipeline that separates anonymization (retain) from hard-delete (remove). - [ ] Build the two-step confirmation modal. - [ ] Schedule the delayed cleanup job and transactional receipt email. Wireframe Mapping: Settings (Wireframe 10). | 0 |  |  |  | 2026-04-18 | 2026-04-22 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/89 | Backlog
modestmag-dev |  |  | Issue | Build-up and design the settings page, so that its UI is visually appealing for the user and easy for them to navigate through. | 27 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/27 | Backlog
modestmag-dev |  |  | Issue | Implement crucial privacy, personalization, and notification settings to optimize the user’s experience as much as possible, making sure they have access to enabling/disabling a variety of features whenever they desire. | 28 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/28 | Backlog
modestmag-dev |  |  | Issue | Create an automated notification system that is able to send over notifications of certain types to users based on their specified preferences in that field. | 29 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/29 | Backlog
mjuliano328 |  |  | Issue | Build popup for when a specific inquiry is clicked, that allows user to read message and has a prompt to reply | 33 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/33 | Backlog
mjuliano328 |  |  | Issue | Create text field for a reply, with ability to send | 34 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/34 | Backlog
mjuliano328 |  |  | Issue | Build UI for completed opportunity dashboard for students/notification of completion for organizations | 36 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/36 | Backlog
mjuliano328 |  |  | Issue | Access database to read/mark completed status of opportunity | 37 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/37 | Backlog
mjuliano328 | mjuliano328 | 2026-04-18 | Issue | US-017 - Save Opportunities to review later (2 story points) | 73 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | User story: As a volunteer, I want to save opportunities I;m interested in to a personal list, so that I can come back and review them before applying. Acceptance Criteria: - [ ] A [Save] button appears on each opportunity card in search results and on the detail page. - [ ] Clicking [Save] adds the opportunity to a "Saved Opportunities" list accessible from the dashboard. - [ ] The button toggles to [Saved] once added, and clicking it again removes it. - [ ] Saved opportunities persist across sessions for the logged-in volunteer. Tasks: - [ ] Add Save/Unsave toggle button to opportunity card and detail view components. - [ ] Create backend endpoint and database table for saved opportunities (user_id, opportunity_id) - [ ] Build a Saved Opportunities list view reachable from the student dashboard. Wireframe Mapping: Opportunity Search and Browse (Wireframe 3); Student Home Dashboard (Wireframe 2). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/73 | Backlog
mjuliano328 | mjuliano328 | 2026-04-18 | Issue | US-019 - Save a draft opportunity before publishing (2 story points) | 75 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Low Priority |  | User Story: As an organization, I want to save an in-progress opportunity posting as a draft so that I can come back and finish writing it before publishing. Acceptance Criteria: - [ ] The Post an Opportunity form shows both [Post Opportunity] and [Save Draft] buttons. - [ ] Draft opportunities are saved without validation on required fields. - [ ] Draft opportunities appear in a "Drafts" section of the organization dashboard, separate from published opportunities. - [ ] A draft can be edited and published later, or deleted. Tasks: - [ ] Add a status enum (draft, published, closed) to the opportunity schema. - [ ] Implement Save Draft handler that skips required-field validation. - [ ] Build a Drafts list on the organization dashboard with Edit and Delete actions. Wireframe Mapping: Post an Opportunity (Wireframe 7); Organization Home Dashboard (Wireframe 4). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/75 | Backlog
mjuliano328 |  |  | Issue | US-024 - View opportunities on an interactive map (3 story points) | 77 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Low Priority |  | User Story: As a volunteer, I want to see opportunities plotted on a map so that I can pick ones close to home or school visually rather than by zip code. Acceptance Criteria: - [ ] A Map toggle on the search page switches between list view and map view. - [ ] Each opportunity with a valid address appears as a pin on the map. - [ ] Clicking a pin opens a card with the opportunity title, organization, and an [Apply] button. - [ ] The map auto-centers on the user&#39;s location if geolocation is granted, otherwise on the New Jersey region. Tasks: - [ ] Integrate a map library (Leaflet or Google Maps) with a basic pin-cluster layer. - [ ] Geocode opportunity addresses at post time and cache lat/long. - [ ] Build the map view component and toggle control. Wireframe Mapping: Opportunity Search &amp; Browse (Wireframe 3); Organization Profile (Wireframe 5). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/77 | Backlog
mjuliano328 |  |  | Issue | US-021 - Upload and change profile avatar (2 story points) | 78 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | User Story: As a user, I want to upload and replace my profile avatar so that my profile feels personal and I&#39;m recognizable to others on the platform. Acceptance Criteria: - [ ] From the profile edit page, users can upload a JPG, PNG, or WEBP image up to 5 MB. - [ ] The uploaded image is cropped to a square and resized to 256x256 before storage. - [ ] The new avatar appears everywhere the user's profile is shown within 30 seconds. - [ ] If no avatar is set, a default avatar with the user's initials is shown instead. - [ ] Users can remove their avatar and return to the default. Tasks: - [ ] Add a file-upload control to the profile edit view. - [ ] Implement server-side image validation, resize, and storage. - [ ] Build a default-initials avatar fallback component. Wireframe Mapping: Student Profile (Wireframe 6); Organization Home Dashboard (Wireframe 4). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/78 | Backlog
mjuliano328 |  |  | Issue | US-022 - Manually add a past experience to profile (2 story points) | 79 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | User Story: As a volunteer, I want to manually add past volunteer or internship experiences that I completed outside this platform so that my full experience history is visible on my profile. Acceptance Criteria: - [ ] From the student dashboard or profile, clicking "+ Add Experience" opens a form capturing: organization name, role, start date, end date, and description. - [ ] Saved manual experiences appear in the profile's Student Experiences section alongside platform-tracked experiences. - [ ] Manual experiences are visually marked as "+ Added manually" to distinguish them from auto- tracked ones. - [ ] Manual experiences can be edited or deleted by their owner. Tasks: - [ ] Add source field (auto, manual) to the experience data model. - [ ] Build Add Experience modal/form with date-range inputs and description text area. - [ ] Update the profile experience list to render the source badge. Wireframe Mapping: Student Profile (Wireframe 6); Student Home Dashboard (Wireframe 2). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/79 | Backlog
mjuliano328 |  |  | Issue | US-023 - Add and edit organization impact metrics (2 story points) | 80 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | User Story: As an organization, I want to add and edit impact metrics displayed on my public profile so that students and partners can see the measurable outcomes of my organization's work. Acceptance Criteria: - [ ] From profile settings, the organization can add up to 6 impact metrics, each with a numeric value and a short label (e.g., "500+ meals served monthly"). - [ ] Metrics are editable and deletable. - [ ] Metrics display in a 3-column grid on the public profile. - [ ] Changes to metrics are visible to other users within 60 seconds. Tasks: - [ ] Design impact_metric schema (organization_id, label, value, display_order). - [ ] Build metric management UI in organization profile settings. - [ ] Update public profile view to render metrics grid. Wireframe Mapping: Organization Profile (Wireframe 5). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/80 | Backlog
mjuliano328 |  |  | Issue | US-025 - Withdraw a submitted application (2 story points) | 81 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | User Story: As a volunteer, I want to withdraw an application I've already submitted so that I can free up organization's review time if my plans change. Acceptance Criteria: - [ ] On the student's Your Applications view, each application with status "Applied" shows a [Withdraw] button. - [ ] Clicking [Withdraw] asks for confirmation before removing the application. - [ ] After withdrawal, the application is removed from the organization's applicant list and the student's active applications list. - [ ] A withdrawn application cannot be re-submitted to the same opportunity for 24 hours (prevents spam). - [ ] The organization receives a notification that the application was withdrawn. Tasks: - [ ] Add withdrawn status to the application state machine. - [ ] Add Withdraw action with confirmation dialog to the Your Applications view. - [ ] Implement the 24-hour re-application cooldown check on submit. Wireframe Mapping: Student Home Dashboard (Wireframe 2). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/81 | Backlog
mjuliano328 |  |  | Issue | US-027 - Log service hours with supervisor verification (5 story points) | 83 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | User Story: As a volunteer, I want to log hours worked on an opportunity and have my supervisor at the organization verify them so that I have a trusted record of service hours for school requirements. Acceptance Criteria: - [ ] From a completed or active experience on their profile, the volunteer can click [Log Hours] and enter a date, hours (decimal), and brief description. - [ ] The log entry appears in an Unverified section on the organization's dashboard under that opportunity. - [ ] The organization supervisor can [Verify] or [Reject] each entry; rejected entries must include a reason visible to the volunteer. - [ ] Verified hours are totaled on the volunteer's profile as &quot;Verified Service Hours&quot;. - [ ] Unverified entries older than 30 days are flagged to the organization. Tasks: - [ ] Design hour_log schema (volunteer_id, opportunity_id, date, hours, description, status, rejection_reason). - [ ] Build the volunteer-side hour entry form and log history view. - [ ] Build the organization-side verification queue with verify/reject actions. - [ ] Update the volunteer profile to sum and display verified hours. Wireframe Mapping: Student Profile (Wireframe 6); Organization Home Dashboard (Wireframe 4). | 0 |  |  |  | 2026-04-18 | 2026-05-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/83 | Ready
nakiwem | nakiwem | 2026-05-12 | Issue | Create Contact Us Page | 104 | CLOSED | drew-csci/opportunity_app_srping_2026 | nakiwem | High Priority |  | As a user (volunteer(student) or organization, I want tob be able to contact the support team through a form so that I can get help, report issues, or ask questions and receive a timely response. Acceptance Criteria: Contact form saves required information (first name, last name, email, message) Allows user to select their role and inquiry type (general, technical, organization) Displays a success confirmation after form is submitted Contact information (email, phone, hours) is visible on the page FAQ section displays and expands inline without leaving the page Implementation Tasks: Build/Design contact page UI with a personal info section (first name, last name, email, role) and inquiry section (subject, message) Implement tab switching for inquiry type with subject pre-fill logic Implement client-side form validation with inline error states Build/Design success confirmation view after form submission Build/Design contact info panel and collapsible FAQ section Story Points: 5 | 0 |  |  |  | 2026-05-11 | 2026-05-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/104 | Ready
NguyenTin2026 | NguyenTin2026 | 2026-03-04 | Issue | US-009 – View peer activity feed of recent experiences | 3 | CLOSED | drew-csci/opportunity_app_srping_2026 | NguyenTin2026 | Medium Priority |  | As a volunteer, I want to view a peer activity feed of recent experiences so that I can see what other volunteers have done and learn from their experiences. Acceptance Criteria: The volunteer can access the activity feed from the dashboard or social section The system displays recent volunteer experiences from other users Each activity shows volunteer name, organization, and experience title The volunteer can scroll through the activity feed If there are no activities, the system displays a message "No recent activity available" Tasks: Build/Design activity feed UI page Connect activity feed to database to retrieve experiences Display activity information in chronological order Ensure the page loads properly and allows scrolling Wireframe Mapping: Student Home Dashboard – Social Feed section | 0 |  |  |  | 2026-02-25 | 2026-05-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/3 | Ready
NguyenTin2026 | NguyenTin2026 | 2026-03-04 | Issue | US-011 – Send messages to organizations with AI-assisted FAQ responses | 5 | CLOSED | drew-csci/opportunity_app_srping_2026 | NguyenTin2026 | Medium Priority |  | As a volunteer, I want to send messages to organizations with AI-assisted FAQ responses so that I can quickly get answers to my questions. Acceptance Criteria: The volunteer can open the messaging section The volunteer can select an organization to message The volunteer can type and send messages The system provides AI-assisted FAQ suggestions The organization receives the message The volunteer can see sent messages in the chat Tasks: Build/Design messaging UI interface Implement message sending functionality Connect messaging system to database Integrate AI-assisted FAQ response feature Ensure messages are stored and displayed properly Wireframe Mapping: Messaging section – Student Dashboard | 0 |  |  |  | 2026-02-25 | 2026-05-12 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/5 | Ready
mjuliano328 |  |  | Issue | US-028 - Organization posts a news update to followers (3 story points) | 84 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | User Story: As an organization, I want to post short news updates that my followers see in their peer activity feed so that I can announce events, milestones, or shout-outs to engaged volunteers. Acceptance Criteria: - [ ] A [Share News Update] button on the org dashboard opens a compose modal with a title (max 80 chars) and body (max 500 chars). - [ ] When posted, the update appears in the peer activity feed of every volunteer who follows this organization. - [ ] The update is also visible in a News section on the organization's profile. - [ ] Organizations can delete their own updates; this removes them from feeds and profiles. Tasks: - [ ] Design news_update schema (organization_id, title, body, created_at). - [ ] Build the compose modal accessible from the org dashboard. - [ ] Extend the peer feed query to include news updates from followed orgs. - [ ] Add a News section to the organization profile view. Wireframe Mapping: Organization Home Dashboard (Wireframe 4); Peer Activity Feed (Wireframe 9); Organization Profile (Wireframe 5). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/84 | Backlog
mjuliano328 |  |  | Issue | US-029 - Filter peer feed to show only new opportunities (1 story point) | 85 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Low Priority |  | User Story: As a volunteer, I want to filter the peer activity feed to only show new opportunity postings so that I can quickly scan what's newly available without wading through social updates. Acceptance Criteria: - [ ] The feed page has a toggle with two states: [All] and [New Opportunities Only]. - [ ] The toggle state persists across page refreshes within the same session. - [ ] When "New Opportunities Only" is selected, only posts of type opportunity_posted are shown. - [ ] The active state of the toggle is visually obvious. Tasks: - [ ] Add feed_filter UI toggle component above the feed. - [ ] Parameterize the feed query by post-type filter. Wireframe Mapping: Peer Activity Feed (Wireframe 9). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/85 | Backlog
mjuliano328 |  |  | Issue | US-030 - Organization manages FAQ content for AI responses (3 story points) | 86 | OPEN | drew-csci/opportunity_app_srping_2026 |  | High Priority |  | User Story: As an organization, I want to write and maintain an FAQ page with common questions and answers so that the AI messaging assistant can respond to volunteer inquiries accurately on my behalf. Acceptance Criteria: - [ ] From the org profile or dashboard, an FAQ management page lets the organization add, edit, reorder, and delete FAQ entries. - [ ] Each entry has a question (max 200 chars) and an answer (max 1000 chars). - [ ] FAQ entries are visible to volunteers on the org&#39;s public profile via an [FAQ] button. - [ ] The same FAQ content feeds the AI response system used in US-011 messaging. - [ ] A preview pane shows how the entry will display to volunteers. Tasks: - [ ] Design faq_entry schema (organization_id, question, answer, sort_order). - [ ] Build the FAQ management CRUD interface for organizations. - [ ] Build public FAQ display linked from the org profile. - [ ] Wire FAQ content into the AI response prompt context. Wireframe Mapping: Organization Profile (Wireframe 5); Messaging / Chat (Wireframe 8). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/86 | Backlog
mjuliano328 |  |  | Issue | US-031 - Rate AI responses as helpful or escalate to a human (2 story points) | 87 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | User Story: As a volunteer, I want to tell the system whether the AI's answer was useful or ask to speak with a real person so that I get the help I actually need when the AI falls short. Acceptance Criteria: - [ ] Every AI-generated response in a chat shows [Yes, thanks] and [Talk to a person] buttons. - [ ] Clicking [Yes, thanks] closes the feedback prompt and logs the AI response as helpful. - [ ] Clicking [Talk to a person] escalates the thread to a human representative at the organization; the original question is delivered with a flag indicating the AI response was insufficient. - [ ] Once escalated, the thread is visible in the organization's inbox and no further AI responses are generated for that thread. Tasks: - [ ] Add helpful_rating column to AI responses in the message thread model. - [ ] Implement the escalation action that transitions the thread state to human_handling. - [ ] Update the org inbox query to include escalated threads with a visual flag. Wireframe Mapping: Messaging / Chat (Wireframe 8). | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/87 | Backlog
mjuliano328 |  |  | Issue | US-032 - Change password while logged in (2 story points) | 88 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | User Story: As a user, I want to change my password while logged in without going through the forgot-password email flow so that I can rotate credentials quickly when I want to. Acceptance Criteria: - [ ] The Settings > Account section has a Change Password control. - [ ] The form requires current password, new password, and new password confirmation. - [ ] The new password must meet the same strength rules as the signup form. - [ ] On success, the user sees a confirmation message and other active sessions are invalidated. - [ ] On failure, a specific error is shown (wrong current password, weak new password, mismatched confirmation). Tasks: - [ ] Build the Change Password form inside Settings > Account. - [ ] Implement backend endpoint that re-authenticates with the current password before updating. - [ ] Add session-invalidation logic for other devices. Wireframe Mapping: Add session-invalidation logic for other devices. | 0 |  |  |  | 2026-04-18 | 2026-04-18 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/88 | Backlog
mjuliano328 |  |  | Issue | Create automatic post on dashboard notifying users of opportunity completion, based on completed status | 38 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-04-22 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/38 | Backlog
mjuliano328 |  |  | Issue | US-036 - Admin reviews and acts on reported content (5 story points) | 92 | OPEN | drew-csci/opportunity_app_srping_2026 | mjuliano328 | High Priority |  | User Story: As an admin, I want a moderation queue where I can review reported content and take action so that I can keep the platform safe and well-functioning. Acceptance Criteria: - [ ] Admin users have access to a dedicated /admin/moderation view not visible to other roles. - [ ] The queue displays open reports sorted by age, with filters for target type and reason. - [ ] Clicking a report shows the reported content in-context with the reporter's notes. - [ ] Available actions include: dismiss report, warn user, hide content, suspend account (3/7/30 days), ban account. - [ ] All actions are logged with the admin's identity and timestamp, and the reporter is notified of the resolution. Tasks: - [ ] Add admin role to the user model with a role-gated route guard. - [ ] Build the moderation queue list view. - [ ] Build the report detail view with the listed admin actions. - [ ] Implement action-logging and reporter-notification emails. Wireframe Mapping: New screen — model layout on Organization Home Dashboard (Wireframe 4) left-nav style. | 0 |  |  |  | 2026-04-18 | 2026-04-30 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/92 | Backlog
modestmag-dev |  |  | Issue | Add a ‘Settings’ listing within the nav portion of each user type’s dashboard, to allow for ease of access to the feature. | 26 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/26 | Backlog