## Project Items
Author | Type | Title | # | State | Repository | Assignees | Labels | Milestone | Body | Comments (#) | Comments | Reviews | Linked PRs / Issues | Created | Updated | URL | Status
dylantomza | Issue | Admin Account Login | 20 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | **User Story** As an admin, I want to be able to log into my account so that I can securely access the platform. **Acceptance Criteria** - The investor can log in - The investor can log out **Tasks** - [ ] Set up database for account information - [ ] Create register API endpoint - [ ] Create login API endpoint - [ ] Create logout API endpoint - [ ] Implement UI for registration, login, logout **Story Points: 8** | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/20 | Backlog
dylantomza | Issue | Company Account Registration & Login | 18 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | **User Story** As a company, I want to be able to create an account so I can securely access the platform. **Acceptance Criteria** - The company can register using the company's name, email, contact person, and password - The company can log in - The company can log out **Tasks** - [ ] Set up database for account information - [ ] Create register API endpoint - [ ] Create login API endpoint - [ ] Create logout API endpoint - [ ] Implement UI for registration, login, logout **Story Points: 8** | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/18 | Backlog
dylantomza | Issue | Investor Account Registration & Login | 19 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | **User Story** As an investor, I want to be able to create an account so that I securely access the platform. **Acceptance Criteria** - The investor can register email, name, and password - The investor can log in and out - The investor can log out **Tasks** - [ ] Set up database for account information - [ ] Create register API endpoint - [ ] Create login API endpoint - [ ] Create logout API endpoint - [ ] Implement UI for registration, login, logout **Story Points: 8** | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/19 | Backlog
csabatino23 | Issue | US-001: Keyword/Opportunity Search | 5 | OPEN | drew-csci/discovery_hub_spring_2026 | csabatino23 | priority: low |  | User Story As a BD Analyst, I want to search opportunities using keywords and filters so that I can identify relevant licensing targets. Acceptance Criteria - Search returns results within 2 seconds - Supports selecting different filters - Supports 100+ results Story Points: 8 Wireframe: opportunity search Tasks - Create search API endpoint - Implement multi-select filter UI - Add relevance score to result cards - Implement pagination logic | 1 | [csabatino23 2026-03-16] Updated to include wireframe |  |  | 2026-03-01 | 2026-03-16 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/5 | Backlog
dylantomza | Issue | University Account Registration & Login | 17 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | **User Story** As a university, I want to be able to create an account so that I securely access the platform. **Acceptance Criteria** - The university can register using the university's name, email, contact person, and password - The university can log in - The university can log out **Tasks** - [ ] Set up database for account information - [ ] Create register API endpoint - [ ] Create login API endpoint - [ ] Create logout API endpoint - [ ] Implement UI for registration, login, logout **Story Points: 8** | 0 |  |  |  | 2026-03-02 | 2026-03-04 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/17 | Backlog
csabatino23 | Issue | US-002: Submission Form | 6 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | User Story As a TTO Manager, I want researchers to submit structured invention disclosures so that new technologies automatically enter the pipeline. Acceptance Criteria - Required fields validated before submission - Confirmation email sent upon submission - Inline error messages displayed for invalid fields Story Points: 8 Wireframe: Invention Disclosure Submission Form Tasks Tasks - Build disclosure form UI - Implement form validation - Trigger confirmation email - Auto-create pipeline card | 1 | [csabatino23 2026-03-16] Updated to include wireframe. |  |  | 2026-03-01 | 2026-03-16 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/6 | Backlog
Twerr123 | Issue | Partnership Portal Page | 1 | CLOSED | drew-csci/discovery_hub_spring_2026 |  |  |  | - COMPANY USER VIEW & UNIVERSITY USER VIEW Search for companies, startups and universities to partner with on the development of a patented invention Can filter by field In the overview of the company pulled by AI you should see patent (granted or pending), patent title/number Description on the project Description on the company or team at university Offer information about what Your role will be in the partnership and what they require You can filter down to partnership type to see what kind of partnership they are leaning towards (research, manufacturing, development, co-ownership | 1 | [Twerr123 2026-03-02] As a company I want to use the partnership portal so that I could find a suitable partner in another company or university to fill a need and work together. |  |  | 2026-02-25 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/1 | In Progress
Twerr123 | Issue | Licensing Discovery Page | 2 | CLOSED | drew-csci/discovery_hub_spring_2026 |  |  |  | - Licensing out view (University/Company) Universities and Companies can license out their patents Filter what companies are seeking What technology they are looking for Description about their company Their patents acquired through licensing Request button - fill in terms and if they accept, brings you to messenger Purchasing License View(Company) Displays available patents Info that proves patent is real (patent #, owner) Filing date, Grant date, Expiration date, Citations How much they are seeking for their patent in terms of money Request button - fill in terms and if they accept, brings you to messenger | 1 | [Twerr123 2026-03-02] As a company or university I want to license out my patents so that I can receive royalties and fees from others successes. |  |  | 2026-02-25 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/2 | In Progress
Twerr123 | Issue | Investor Outreach Page | 3 | CLOSED | drew-csci/discovery_hub_spring_2026 |  |  |  | - Investor View AI Investment Fit - AI calculates for investor whether it would be a good match by returning check mark or X with reasons why it wouldn't AI could also calculate the risk( low, medium, high) Info about company to see credibility and patent information Market Size - so investors could determine its potential Shows funding needed Also what the funding will go towards | 1 | [Twerr123 2026-03-02] As a investor , I want to use an investment outreach feature so that I can calculate the best company for me to allocate my money into using AI. |  |  | 2026-02-25 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/3 | In Progress
Twerr123 | Issue | Patent invention Feed | 4 | CLOSED | drew-csci/discovery_hub_spring_2026 |  |  |  | - Displays patented ideas - Video format - People can like and react - Companies/Universities can post. Investor is view only - People from there can message to potentially match on their own without AI - AI can show whats hot in the feed and most popular | 0 |  |  |  | 2026-02-25 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/4 | In Progress
csabatino23 | Issue | US-003: Keyword Watchlists with Alerts | 7 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | User Story As a BD Analyst, I want to create keyword watchlists so that I receive alerts when new matching opportunities appear. Acceptance Criteria - User can create up to 20 watchlists - Daily or weekly options - Alerts link directly to matched records - Watchlists can be enabled or disabled Story Points: 5 Wireframe: Opportunity Search & Browse Tasks - Create watchlist data model - Build alert configuration UI - Implement scheduled email job - Add enable/disable toggle | 1 | [csabatino23 2026-03-16] Updated to include wireframe. |  |  | 2026-03-01 | 2026-03-16 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/7 | Backlog
Twerr123 | Issue | Patent Library Assistant | 21 | CLOSED | drew-csci/discovery_hub_spring_2026 |  |  |  | As a company, I want to ask whether a certain patented idea exists so that I can know for my own projects. - Accesses patent database - Can navigate easier by querying the Ai assistant for a specific field - Can ask questions about patents | 0 |  |  |  | 2026-03-02 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/21 | In Progress
Twerr123 | Issue | Investment Analyzer | 22 | CLOSED | drew-csci/discovery_hub_spring_2026 |  |  |  | As an investor, I want to evaluate patents and licensing activity so that I can identify promising companies and technologies worth investing in. - Used to evaluate risk - The amount of patents the company has - How relevant their patents are - View patent credibility and strength - Patent count | 0 |  |  |  | 2026-03-02 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/22 | In Progress
Twerr123 | Issue | Company Inquiry Page | 23 | CLOSED | drew-csci/discovery_hub_spring_2026 |  |  |  | As a company I want to be able to use the company Inquiry page to view the inventors in a specific company and narrow it down to the inventors for that patent. - Good for hiring from that company - If you want to get personal feedback or need some sort of inspiration - Questions on patented work | 0 |  |  |  | 2026-03-02 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/23 | In Progress
Twerr123 | Issue | Administrator View | 24 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | As an administrator, I want to manage users, data, and system settings so the platform runs reliably and securely. - Database of things such as companies, universities, patents - User views - Secure environment | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/24 | Backlog
Twerr123 | Issue | Partnership Portal Page | 25 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | Role: Company or University User Story As a company I want to find another company to collaborate with so that I could get expertise in a specific area related to the development of an invention. AC - Can filter the partnership type (manufacturer, research, Co-ownership, licensing) - Specify the industry that your in - Company background - What you need in a partnership - AI finds a match for you based on your needs Tasks - Build UI - Need to set up API - Need a database | 0 |  |  |  | 2026-03-13 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/25 | Backlog
Twerr123 | Issue | Innovation Feed Page | 26 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | User Role: Company, University, Investor User Story As a user on this site I want to be able to see videos of people displaying their patented ideas so that I could get inspired and potentially reach out to them. AC - Has create a post button - View Videos/Pictures - Underneath the post the company or university profile gets automatically inserted Tasks - Build Innovation Feed UI - Implement create post functionality - Add media upload (video/image) - Create post database model - Display posts in feed - Attach organization profile to posts - Restrict posting by role - Test feature | 0 |  |  |  | 2026-03-13 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/26 | Backlog
Twerr123 | Issue | Patent Library Assistant | 27 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | Users Role: Company, Investor, University As any user I want to be able to do quick patent research so that I could gain information related to what I'm looking for. AC - User can enter a patent research question in the AI assistant - System returns relevant patent information or summaries - User can view basic patent details (title, inventor, owner, summary) - Results display in a readable list or response format Tasks - Build Patent Library Assistant UI - Add input field for research questions - Implement backend endpoint for patent search/analysis - Fetch and display patent results - Format results with key patent details - Test assistant responses and results display | 0 |  |  |  | 2026-03-13 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/27 | Backlog
Twerr123 | Issue | Discovery Page | 28 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | User Role: Investor As an investor I want to find new companies that need funding so that I could potentially gain from their profits and success while funding them. AC - Investor can view a list of companies seeking funding - Investor can filter companies by industry/field - Investor can filter companies by patent count - Investor can filter companies by company stage (new or experienced) - Investor can open a company profile to view details - Investor can press a Risk Calculator button to evaluate the company - System displays Low, Medium, or High risk based on company information Tasks - Build Discovery Page UI - Display list of companies seeking funding - Add filter for company industry/field - Add filter for patent count - Add filter for company stage (new/experienced) - Create company profile view page - Implement Risk Calculator button - Implement AI/backend logic for risk calculation - Display risk result (Low / Medium / High) - Test filters and risk calculator functionality | 0 |  |  |  | 2026-03-13 | 2026-03-13 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/28 | Backlog
gshen1-SGZ | Issue | Customized Patent Activity Alerts for Investors | 29 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | User Story As an investor, I want to set up customized alerts for patent activity in specific industries so that I can be notified when promising startups or companies are filing new patents and act quickly on investment opportunities. Acceptance Criteria - Filter alerts by industry, technology category, or company size - Receive notifications when new patents match alert criteria - View a summary of new filings and its value - Save and compare companies flagged by alerts Tasks - Build alert configuration UI with industry/category/company size filters - Implement notification system for patent activity triggers - Create filing summary dashboard view - Add company save and comparison feature Story Points: 8 | 0 |  |  |  | 2026-03-15 | 2026-03-15 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/29 | Backlog
gshen1-SGZ | Issue | Patent Licensing Marketplace for University Students | 30 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | User Story As a university student, I want to use the patent licensing marketplace so that I can list my available patents for companies to discover and license, to generate revenue to fund further research. Acceptance Criteria - Upload and manage patent listing - Set licensing terms and pricing - Track which companies have viewed or expressed interest in patents - Receive licensing requests through the platform Tasks - Build patent listing upload and management interface - Implement licensing terms and pricing configuration - Create company interest tracking and analytics view - Develop licensing request inbox and notification system Story Points: 5 | 0 |  |  |  | 2026-03-15 | 2026-03-15 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/30 | Backlog
gshen1-SGZ | Issue | Administrator Patent Data Review and Verification | 31 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | User Story As an administrator, I want to review and verify the accuracy of patent data submitted by users so that the platform maintains high data quality and trustworthiness for all users. Acceptance Criteria - Flag suspicious or duplicate patent entries - Approve or reject user-submitted patent updates - Generate data quality reports by category or date range Tasks - Build admin review queue for submitted patent data - Implement flag system for suspicious or duplicate entries - Create approve/reject workflow for patent updates - Develop data quality report generation by category and date range Story Points: 8 | 0 |  |  |  | 2026-03-15 | 2026-03-15 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/31 | Backlog
gshen1-SGZ | Issue | Patient Data Showcase for University Students (Cadence) | 32 | OPEN | drew-csci/discovery_hub_spring_2026 |  |  |  | User Story As a university student, I want to be able to use the website to be able to showcase patient data: Cadence. Acceptance Criteria - Upload and manage patient name and health information - Search bar to find patient - Summary created of patient health Tasks - Build patient data upload and management interface - Implement patient search bar with name/health filters - Create automated patient health summary generation view Story Points: 3 | 0 |  |  |  | 2026-03-15 | 2026-03-15 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/32 | Backlog
paolareyes-rgb | Issue | Meeting Scheduler | 33 | OPEN | drew-csci/discovery_hub_spring_2026 | paolareyes-rgb |  |  | User Story As a Business Development Analyst, I want to schedule meetings directly from a match card so that partnership discussions happen faster. **Acceptance Criteria** Integration with Google Calendar and Outlook Users can propose meeting times Confirmed meetings create calendar events Meeting notes logged in associated deal record **Story Points: 8** **Tasks** Implement authentication Build scheduling interface Create calendar event integration Link meeting notes to deal record | 0 |  |  |  | 2026-03-18 | 2026-03-18 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/33 | Backlog
paolareyes-rgb | Issue | Export PDF Summary | 34 | OPEN | drew-csci/discovery_hub_spring_2026 | paolareyes-rgb |  |  | **User Story** As a Business Development Analyst, I want to export a one-page deal summary PDF so that I can share updates with stakeholders. **Acceptance Criteria** Includes deal title, partner names, stage, and key dates Includes financial terms (if entered) Generates within 10 seconds **Story Points: 5** **Tasks** Create PDF template Implement PDF generation service Populate deal data dynamically Add export button | 0 |  |  |  | 2026-03-18 | 2026-03-18 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/34 | Backlog
paolareyes-rgb | Issue | Patent Search Attached to Disclosure | 35 | OPEN | drew-csci/discovery_hub_spring_2026 | paolareyes-rgb |  |  | **User Story** As a Technology Transfer Office Manager, I want to search patents from within a disclosure record so that IP context is easily accessible. **Acceptance Criteria** Displays patent number, title, assignee, status Patents can be pinned to disclosure with notes Activity logged **Story Points: 8** **Tasks** Integrate patent API Build patent result display UI Implement pin-to-record function Add activity logging | 0 |  |  |  | 2026-03-18 | 2026-03-18 | https://github.com/drew-csci/discovery_hub_spring_2026/issues/35 | Backlog