## Project Items
Author | Edited By | Last Edited | Type | Title | # | State | Repository | Assignees | Labels | Milestone | Body | Comments (#) | Comments | Reviews | Linked PRs / Issues | Created | Updated | URL | Status
vlad-im | vlad-im | 2026-03-07 | Issue | Custom event mob framework | 31 | OPEN | drew-csci/minecraft_mod_spring_2026 |  |  |  | User Story: As a player I want to experience "raid" events, which are randomly triggered at night, and pose a significant threat and challenge, so that the game is not predictable and I have a goal to beat the event and survive. Acceptance Criteria: - Create MobEventManager class. - Implement event registration system. - Add timed event scheduler. - Add random event selector logic (with escalating odds). - Add a grace period before the event can start happening randomly. - Add admin command /startEvent. Tasks: - The event starts in an unpredictable pattern. - The event does not start before the grace period ends. - The event can be triggered manually (mostly for testing). Story Points: 5 | 0 |  |  |  | 2026-03-07 | 2026-03-07 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/31 | Backlog
elikhovid | vlad-im | 2026-03-07 | Issue | Super Enchantment table upgrade | 22 | OPEN | drew-csci/minecraft_mod_spring_2026 |  |  |  | User Story: As a player, I want a Super Enchantment Table upgrade, so I can access stronger and more specialized enchantments in the late game. Acceptance Criteria: - Player can craft or unlock the Super Enchantment Table through progression - Super Enchantment Table allows stronger or exclusive enchantments (Example: sharpness VII) - Upgrade requires rare new materials (from the mob drops) to prevent early-game access. - Table has a new texture with visual effects. - Using the table provides visual and audio feedback. Tasks: - Clear and defined crafting recipes (or unlock condition). - Clear and defined exclusive enchantments available. - Adjusted price requirements for new, upgraded enchantments. (Lapis Lazuli). - Create new texture/model for the upgraded table. - Balance enchantment power for late-game. Story Points: 5 | 0 |  |  |  | 2026-03-04 | 2026-03-07 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/22 | Backlog
elikhovid | vlad-im | 2026-03-07 | Issue | Add New High-Tier Items | 20 | OPEN | drew-csci/minecraft_mod_spring_2026 |  |  |  | #TODO Dmitry User Story: As a player, I want to have new high-tier items to be added, so I can gain powerful late-game gear and rewards for surviving dangerous events. Acceptance Criteria: - New high-tier items are obtainable through intended late-game progression. - Items provide stronger stats or unique effects compared to existing gear. - Items have custom textures, names, and descriptions - Items can be used in combat, exploration, or survival scenarios Tasks: - Define stats for new items - Implement crafting recipes OR mob-only drops - Add item textures/models(maybe) - Balance durability & damage Story Points: 5 | 0 |  |  |  | 2026-03-04 | 2026-03-07 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/20 | Backlog
elikhovid | jantonacci-svg | 2026-03-04 | Issue | World Event (The Crimson Descent) | 24 | OPEN | drew-csci/minecraft_mod_spring_2026 |  | Difficulty: Hard, Priority: High |  | Title: World Event (The Crimson Descent) As a player i want a new event to come to Minecraft to make it fun and exciting. The traditional game lacks new experiences. Here is a rough idea of what the new event should look like. Image: <img width="1536" height="1024" alt="Image" src="https://github.com/user-attachments/assets/f0822f57-3dee-41db-a246-7b9e88a3010a" /> Story Points: 8 Acceptance Criteria: 1.) Occurs once every week. 2.) Chances of it happening are based on probability. The day it can occur on is completely random. 3.) Add new type of sky color (red). 4.) Increase mob spawn on these nights. Task: 1.) add an internal timer to set off the event. 2.) scale the probability of the event occurring each day. 3.) add new textures to the game 4.) increase mob spawn rate. | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/24 | Ready
elikhovid | MaxConk | 2026-03-04 | Issue | New Boss Creation (Void Devourer) | 25 | OPEN | drew-csci/minecraft_mod_spring_2026 |  |  |  | User Story: As a player, I want a new boss to spawn after I defeat the Ender Dragon and summon it, so I can access challenging late-game content. Acceptance Criteria: - Boss spawns after the player summons it (by destroying the Ender Dragon egg) - Summoning provides visual and audio feedback - Boss spawns near player spawn - Boss difficulty is scaled to difficulty Tasks: - Define Boss name (Void Devourer) - Define Boss abilities (damage, movement, and special attacks) - Set Boss health - Create texture and sound effects for the boss Story Points: 8 <img width="1536" height="1024" alt="Image" src="https://github.com/user-attachments/assets/e61f05f7-d48c-4ca1-8313-6d1348240e04" /> | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/25 | Backlog
elikhovid | LKleva | 2026-03-04 | Issue | Add Post-End Exclusive Mobs | 14 | OPEN | drew-csci/minecraft_mod_spring_2026 |  | Difficulty: Hard, Priority: High |  | TITLE: Post-End Exclusive Mobs As a player, I want to have unique mobs spawn post end, so that there are unique mobs and an increased difficulty. Tasks: Design stats for several new mobs Implement mob AI behavior Add spawn rules (post-End only) Implement loot table Acceptance Criteria: New mobs created Mobs have loot table Spawns have rules Story Points: 5 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/14 | Backlog
elikhovid | LKleva | 2026-03-04 | Issue | Create Player Progression Metric | 15 | OPEN | drew-csci/minecraft_mod_spring_2026 |  | Difficulty: Easy, Priority: High |  | TITLE: Player Progression As a player, I want there to be a scalable metric for progression, so that the difficulty increases as I advance Tasks: Define progression score formula (milestones, gear tier, bosses defeated) Implement score calculation function using achievements Log progression score to console for testing Acceptance Criteria: Have a score formula Track per advancements Have a command to test the progression Story Points: 2 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/15 | Backlog
elikhovid | LKleva | 2026-03-04 | Issue | Dynamic Mob Scaling System | 16 | OPEN | drew-csci/minecraft_mod_spring_2026 |  | Difficulty: Hard, Priority: High |  | TITLE: Dynamic Mob Scaling As a player, I want the mobs to scale with progression, so that the difficulty expands as I progress more. Tasks: Scale mob HP based on progression score Scale mob damage output Add difficulty caps (min/max limits) Add config file to tune scaling multipliers Acceptance Criteria: Difficulty Caps for mobs Scale damage/hp based on advancement progress Story Points: 3 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/16 | Backlog
elikhovid | LKleva | 2026-03-04 | Issue | Boss Scaling Logic | 17 | OPEN | drew-csci/minecraft_mod_spring_2026 |  | Priority: Medium, Difficulty: Medium |  | TITLE: Boss Scaling As a player, I want the bosses to scale after I beat it, so that when I rematch it the difficulty increases. Tasks: After boss defeat, increment boss tier Scale stats per tier Acceptance Criteria: Boss HP/Damage increases per defeat Story Points: 2 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/17 | Backlog
elikhovid | elikhovid | 2026-03-04 | Issue | Add Advanced AI Behaviors | 18 | OPEN | drew-csci/minecraft_mod_spring_2026 |  | Priority: Medium, Difficulty: Hard |  | As a player, I want enemies to not just run towards me, but be able to do a variety of things, so that the combat feels more challenging and varied. Tasks: Implement dodge behavior Implement block destruction behaviour Implement the ability to climb walls Add group coordination behavior Acceptance Criteria: There is a variety of mobs present, each with its unique abilities The player does not feel completely safe at all times "Cheesing" enemies is prevented Story Points: 5 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/18 | Backlog
elikhovid | elikhovid | 2026-03-04 | Issue | Increase Mob Variety | 19 | OPEN | drew-csci/minecraft_mod_spring_2026 |  | Priority: Medium, Difficulty: Hard |  | As a player, I want more mob variety, so that there is more variety when fighting enemies. Tasks: Create elite (Charged) mob variants Add random modifiers (speed, regen, fire aura) Add visual indicator for elite mobs (Charged Creeper aura) Acceptance Criteria: Certain mobs have charged variant in-game Unique effects on these mobs Story Points: 3 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/19 | Backlog
elikhovid | elikhovid | 2026-03-07 | Issue | Post-End Activation Control | 27 | OPEN | drew-csci/minecraft_mod_spring_2026 |  |  |  | As an admin, I want to have tolls such as config file and commands, so that I can precisely control and test how the mod works. Tasks: Add config option: postEndMode (auto/manual/disabled) Add admin command /triggerPostEnd Add admin command /revertPostEnd Persist override state to world save Acceptance Criteria: The world state can be changed on demand (with appropriate access) The reverse does not break the game, the mod, or corrupt the save file. Story Points: 3 | 0 |  |  |  | 2026-03-04 | 2026-03-07 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/27 | Backlog
elikhovid | LKleva | 2026-03-04 | Issue | Create Difficulty-Based Loot Multiplier | 21 | OPEN | drew-csci/minecraft_mod_spring_2026 |  | Difficulty: Medium, Priority: High |  | As a player, I want mob loot to increase with progression, so that the loot I get when defeating mobs upgrades with my progression Tasks: Link loot drop quality to progression score Implement rarity tiers Add drop rate balancing logic Acceptance Criteria: Link loot drops to progression Have rarity tiers (mob drop %s) Balance drops Story Points: 2 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/21 | Backlog
elikhovid | elikhovid | 2026-03-04 | Issue | Combat Rebalance | 23 | OPEN | drew-csci/minecraft_mod_spring_2026 |  |  |  | As a player, I want to experience updated combat system, so as to make it more challenging and varied. Tasks: Reduce player base regen speed Increase mob aggression radius Add punish mechanics (combo damage, status effects) Acceptance Criteria: Combat feels new Most of the enemies pose a challenge and are not a push over Story Points: 5 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/23 | Backlog
elikhovid | elikhovid | 2026-03-04 | Issue | Mob Scaling Controls | 26 | OPEN | drew-csci/minecraft_mod_spring_2026 |  |  |  | As an admin I want to be able to control game difficulty via scaling multipliers and other sliders, through a config file. Tasks: Create DifficultyConfig file (JSON/TOML) Add parameters: HP multiplier, damage multiplier, spawn multiplier Implement runtime config loader Add config validation (min/max bounds) Add /reloadmodconfig command Acceptance Criteria: Config is concise and readable Changing the values does not bug or crash the game Story Points: 3 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/26 | Backlog
elikhovid | MaxConk | 2026-03-04 | Issue | Implement Human-Readable Config | 29 | OPEN | drew-csci/minecraft_mod_spring_2026 |  |  |  | User Story: As a player, I want the configuration file to be easy to read and modify so I can customize the mod without confusion. Acceptance Criteria: - All parameters and settings are clear and easy to understand - Config is organized by setting - Default settings are set (player has the option to use) Tasks: - Identify all parameters - Verify default settings - Confirm valid ranges - Organize by section of setting - Create GUI - Implement selected settings into the game Story Points: 5 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/29 | Backlog
elikhovid | MaxConk | 2026-03-04 | Issue | Documentation | 30 | OPEN | drew-csci/minecraft_mod_spring_2026 |  |  |  | User Story: As a user, I want a clear configuration section in the README so I can easily understand and customize the mod’s settings. Acceptance Criteria: - A configuration section exists - All settings that affect performance are clearly marked - Settings are customizable Tasks: - Identify all config parameters (difficulty, scaling, spawns, etc). - Verify and confirm valid ranges - Create a GUI that is clear and easy to understand. Story Points: 3 | 0 |  |  |  | 2026-03-04 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/30 | Backlog
jantonacci-svg | jantonacci-svg | 2026-03-04 | Issue | Boss Scaling Control | 7 | OPEN | drew-csci/minecraft_mod_spring_2026 |  | Priority: Medium, Difficulty: Hard |  | Title: Hostile Mobs Scaling Control As a player, I want hostile mobs to scale only after milestones so early gameplay is fair. I don't want to be greeted by overpowered mobs that instantly obliterate me. Story Points: 5 Acceptance Criteria: 1.) Hostile mobs will scale with progression of the player. 2.) Add a grace period of 2 days just so the player can get settled. Task: 1.) Scale difficulty on total experience gains and total hostile mob kills. | 0 |  |  |  | 2026-02-28 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/7 | Backlog
jantonacci-svg | MaxConk | 2026-03-04 | Issue | Post-End World Changes | 8 | OPEN | drew-csci/minecraft_mod_spring_2026 |  |  |  | User Story: As a player, I want the world to change after defeating the Ender Dragon so post-End feels fresh. Acceptance Criteria: - Activation gives player feedback(message or sound, etc) - New world altercations occur (Mob variants, new structures, altered spawn rates, etc.) - difficulty progression - Can be toggled in config Tasks: - Give the player a message or indicate activation - Define what changes after Ender Dragon defeat (new boss, stronger/new mobs, hordes, etc.) - Whether changes (environmental events) - Add setting to config Story Points: 8 | 0 |  |  |  | 2026-02-28 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/8 | Backlog
jantonacci-svg | jantonacci-svg | 2026-03-04 | Issue | Create/Add New Items | 11 | OPEN | drew-csci/minecraft_mod_spring_2026 |  | Priority: Medium, Difficulty: Hard |  | New Items: ~~~~~~~~~~ As a player, I want additional items to support the new difficulty system, so progression feels smoother. Items such as new armor or weapons would be great. Acceptance Criteria: 1.) Items will not be overpowered or cause player to feel a sense of boredom. 2.) Item can be spawned in while in creative mode and is craftable in creative. 3.) Item can be enchanted like a normal base-game item. Story points: 3 Task: 1.) Scale new items reasonably. 2.) Make recipes for new items. 3.) Make items capable of receiving enchantments. | 0 |  |  |  | 2026-02-28 | 2026-03-04 | https://github.com/drew-csci/minecraft_mod_spring_2026/issues/11 | Backlog