## Project Items
Author | Type | Title | # | State | Repository | Assignees | Labels | Milestone | Body | Comments (#) | Comments | Reviews | Linked PRs / Issues | Created | Updated | URL | Status
bjach04 | Issue | Search and filter volunteer/internship opportunities | 1 | OPEN | drew-csci/opportunity_app_srping_2026 |  | High Priority |  | As a volunteer, I want to be able to search and filter volunteer and internship opportunities using keywords that apply the filters (such as location, cause, duration, skills) so that I can quickly find positions that would match my interests. Acceptance criteria: Given I am on the opportunities page. When I enter a keyword in the search bar. Then the system displays opportunities that match the keyword. Implementation: Build/Design the search input/handling Implement the filtering method Display the filtered result Story Points: 3 | 0 |  |  |  | 2026-02-25 | 2026-03-03 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/1 | Backlog
bjach04 | Issue | Post new volunteer or internship opportunities | 2 | OPEN | drew-csci/opportunity_app_srping_2026 |  | High Priority |  | As an organization user, I want to create and publish new volunteer or internship opportunities by providing detailed information such as the role description, required skills, location, duration, and application deadline, so that qualified volunteers can understand the role. Acceptance Criteria: Given I am logged in as a organization user When I navigate to the dashboard Then I can see an option to “Post New Opportunity” Implementation: Implement “Post new opportunity” access in the Organization dashboard Build/design UI and functions for opportunity creation form. Build confirmation and listing update. Story Points: 5 | 0 |  |  |  | 2026-02-25 | 2026-03-03 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/2 | Backlog
bjach04 | Issue | Follow organizations and subscribe to updates | 4 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | As a volunteer, I want to follow organizations and subscribe to their updates so that I can stay informed about new opportunities, events, and announcements that match my interests. Acceptance Criteria: Given I am logged in as a volunteer When I visit an organization’s profile page Then I can click a “Follow” button to follow the organization Implementation: Implement follow/unfollow functionality Display followed organizations “Organizations I Follow” Implement notification system for updates Manage follow/subscription preferences Story Points: 5 | 0 |  |  |  | 2026-02-25 | 2026-03-03 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/4 | Backlog
devhirpara29 | Issue | Volunteer Dashboard | 15 | OPEN | drew-csci/opportunity_app_srping_2026 |  | High Priority |  | As a student volunteer, I want a personalized home dashboard that shows recommended volunteer opportunities and quick actions so that I can easily find opportunities that match my interests and quickly manage my application, profile and experiences from one place. Acceptance Criteria:- 1)The dashboard shows recommended volunteer opportunities 2) I can quickly access my applications, profile and experience section 3) The dashboard should feel simple and helpful not cluttered Implementation Task:- (Story Points-5) 1)Create a student home dashboard page. 2)Add a recommended opportunity section with an Apply button. 3) Add a quick access button for Applications, profile and experience. Wireframe:- Student Home Dashboard | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/15 | Backlog
devhirpara29 | Issue | Organization Dashboard | 16 | OPEN | drew-csci/opportunity_app_srping_2026 |  | High Priority |  | As an organization, I want a home dashboard that gives me an overview of recent applications so that I can quickly review applications, view student details and accept or decline volunteers while easily navigating to my profile, messages and posted opportunities. Acceptance Criteria:- 1. The dashboard shows recent application . 2. I can quickly view applicants details and take action either Accept or Decline. 3. I can easily navigate to my profile, messages and posted opportunities. Implementation Task:- (Story Points- 5) 1. Create a organization home dashboard page 2. Show a recent application list 3. Add accept or decline buttons for each applicant. 4. Add easy navigation to profile, Messages and posted opportunities. Wireframe:- Organization Home Dashboard | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/16 | Backlog
mjuliano328 | Issue | US-012: Receive and Respond to Volunteer Inquiries (5 story points) | 31 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Medium Priority |  | User Story: As an organization, I want to access the messages from student volunteers which have been sent to me and respond to them, so that I can be in open communication with those willing to participate in my organization. Acceptance Criteria: - [ ] Organization should be able to open an inbox and see inquiries, sorted by time of sending - [ ] Should have graphic on UI that displays number of unread inquiries in inbox - [ ] Should be able to open individual messages to read them - [ ] Create a “read” receipt (?) - [ ] Text field to write a reply, ability to send message privately to volunteer - [ ] Character limit (?) - [ ] Helpful message for when text field is empty (or character limit is exceeded) Tasks: - [ ] Build UI for inbox page for organizations, including inquiries sorted by date of receipt - [ ] Build popup for when a specific inquiry is clicked, that allows user to read message and has a prompt to reply - [ ] Create text field for a reply, with ability to send | 0 |  |  |  | 2026-03-02 | 2026-03-04 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/31 | Backlog
mjuliano328 | Issue | Build UI for inbox page for organizations, including inquiries sorted by date of receipt | 32 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/32 | Backlog
mjuliano328 | Issue | Build popup for when a specific inquiry is clicked, that allows user to read message and has a prompt to reply | 33 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/33 | Backlog
mjuliano328 | Issue | Create text field for a reply, with ability to send | 34 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/34 | Backlog
mjuliano328 | Issue | US-010: Post and Share Completed Volunteer Opportunities (3 Story Points) | 35 | OPEN | drew-csci/opportunity_app_srping_2026 |  | Low Priority |  | User Story: As a student, I want to post opportunities which I have completed, so that other users can see what experience I have Acceptance Criteria: - [ ] Can access separate dashboard that contains completed opportunities - [ ] Option to mark opportunity as complete - [ ] Organization can approve or deny that the opportunity is completed - [ ] When approved, create dashboard post that says the opportunity is completed - [ ] When denied, privately notify student of denial Tasks: - [ ] Build UI for completed opportunity dashboard for students/notification of completion for organizations - [ ] Access database to read/mark completed status of opportunity - [ ] Create automatic post on dashboard notifying users of opportunity completion, based on completed status | 0 |  |  |  | 2026-03-02 | 2026-03-04 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/35 | Backlog
mjuliano328 | Issue | Build UI for completed opportunity dashboard for students/notification of completion for organizations | 36 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/36 | Backlog
mjuliano328 | Issue | Access database to read/mark completed status of opportunity | 37 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/37 | Backlog
mjuliano328 | Issue | Create automatic post on dashboard notifying users of opportunity completion, based on completed status | 38 | OPEN | drew-csci/opportunity_app_srping_2026 |  |  |  |  | 0 |  |  |  | 2026-03-02 | 2026-03-02 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/38 | Backlog
modestmag-dev | Issue | (Ryan DeVita) Account Registration/Login Management (Estimate: 3 Story Points) | 19 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev | High Priority |  | ### **User Stroy:** As a user of the Opportunity System, I want to be allowed to create/log into an account tied to my specific role (Organization/Volunteer) and later be able to manage the password that is associated with it, so that I can access my personalized data that is linked with my profile (such as any offerings I have set up or specific opportunities I have access to depending on my role), identify myself properly for other users to see, and regain control over my account in the case that I forget my password (or want the ability to reset it for any other reason). ### **Acceptance Criteria:** - After clicking on the login selection of the website, a user is then presented with two buttons that they can click to indicate whether or not they are a Student (or Volunteer) or an Organization User, and upon clicking a button, the user is sent to the login page associated with their role. - Each login page allows the user to input their email and password into two field boxes, with a login button placed below them that allows them to sign into their account. - Extra links below the login box that direct the user to either create a new account (if not set up already) or reset their password are accessible. - When resetting a password, a user can enter their email into a field, which will then send a confirmation link to it if it is validated as the one linked to their account. Clicking on the link lets the user type in a new password and confirm it to change the password successfully. - A button on the original password reset page below the email field, when clicked, returns the user to their respective login page. - On the Create Account flow, a user is prompted to enter their email and initial password, alongside an extra password validation field just in-case. - Upon account creation and login, the user is directed to their home dashboard, where they can manage their personal account information and such. - Each page within the login process can also be confirmed by pressing the enter key alongside pressing the on-screen button. - Buttons and other login elements are located on the center of the screen and evenly spaced, for ease of access. - If the user fails to enter their login details correctly 10 times, they are locked out from logging in for a short 10-minute period. - Users are logged out of their account after 30 minutes of website inactivity. - Pages take under 5 seconds to load-in properly. - SQL injection and cross-site scripting attempts are rejected by the password field for security. - Incorrectly entered/non-existing info returns a mis-match message to the user. ### **Tasks:** - Build-up and design generalized UI for the login/create account/reset password workflows. - Create the HTML-based login-related forms that check for account information to validate it in real-time for existing account logins, store account information for new accounts, and initiate a password reset for an account if requested (each with enter key functionality and injection/scripting security measures). - Implement the whole reset password workflow properly, by allowing automated password reset emails to be sent to correct email addresses for the process to progress. - Add page redirects to the user’s main homepage upon successfully logging into their account. **Wireframe: Welcome & Login (Wireframe 1)** | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/19 | Backlog
modestmag-dev | Issue | Build-up and design generalized UI for the login/create account/reset password workflows. | 20 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/20 | Backlog
modestmag-dev | Issue | Create the HTML-based login-related forms that check for account information to validate credentials, store information entered in, and allow for password resets to occur (with proper security measures implemented). | 22 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/22 | Backlog
modestmag-dev | Issue | Implement the whole reset password workflow properly, by allowing automated password reset emails to be sent to correct email addresses for the process to progress. | 23 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/23 | Backlog
modestmag-dev | Issue | Add page redirects to the user’s main homepage upon successfully logging into their account. | 24 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/24 | Backlog
modestmag-dev | Issue | (Ryan DeVita) Notification and Privacy Configuration (Estimate: 4 Story Points) | 25 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev | Medium Priority |  | ### **User Story:** As a user of the Opportunity System, I want to be able to access a settings page for my account that allows for me to toggle notifications and privacy features that are linked to it on and off, so that way I can configure how others see my profile and how I am notified about information to my liking. ### **Acceptance Criteria:** - Within the dropdown menu that appears near a user’s profile area, a ‘Settings’ selection is present which allows users to control their overall experience using the website through privacy, notification, and other important options. - There are multiple sub-tabs within the settings page that allows the user to access hyper-specific settings they are looking for, keeping things relatively organized. - In the ‘Notifications’ sub-tab, there are toggle buttons for both update and general notifications (email for both forms of the service and push for the mobile app exclusively, though can still be toggled on desktop just in-case) that the user can turn on and off at any time. - If enabled, email notifications are sent to the email associated with the user’s account, while push notifications are sent as pop-up notifications (different based on phone’s system preferences) to the device that the app is associated with. Update notifications can be added to the pool based on that toggle’s setting, but matching notifications and messages you have received are included in this pool by default. - In the ‘Privacy’ settings, there is a toggle button that can also be turned on and off at will, which enables or disables whether or not a Volunteer’s completed experiences are publicly visible (a setting exclusive for students specifically). A plethora of other privacy options (such as cookies management options and account history settings) should also be manageable in the same fashion for all accounts. - In the ‘Personalization’ section, a toggle button that enables and disables a dark and light visual theme is present to offer users with simple customization options that help them feel the most comfortable using the system. Other personalization options (such as text size, for instance) can also be toggled through dropdown menu options and the like. - A friendly, simplistic UI is implemented where setting types are listed out on the left side of the page, while togglable options are displayed as simple buttons that change color based on your selected theme. All buttons and dropdown menus are designed to fit the general appearance of this screen as cleanly as possible. ### **Tasks:** - Add a ‘Settings’ listing within the nav portion of each user type’s dashboard, to allow for ease of access to the feature. - Build-up and design the settings page, so that its UI is visually appealing for the user and easy for them to navigate through. - Implement crucial privacy, personalization, and notification settings to optimize the user’s experience as much as possible, making sure they have access to enabling/disabling a variety of features whenever they desire (while also adding the Volunteer specific setting to enable and disable experience completion public listings and making sure it is exclusive to those types of users). - Create an automated notification system that is able to send over notifications of certain types to users based on their specified preferences in that field. **Wireframes: Settings - (Wireframe 10) ALONG WITH Student Home Dashboard - (Wireframe 2) and Organization Dashboard - (Wireframe 4) (Last two wireframes specifically for the first task).** | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/25 | Backlog
modestmag-dev | Issue | Add a ‘Settings’ listing within the nav portion of each user type’s dashboard, to allow for ease of access to the feature. | 26 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/26 | Backlog
modestmag-dev | Issue | Build-up and design the settings page, so that its UI is visually appealing for the user and easy for them to navigate through. | 27 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/27 | Backlog
modestmag-dev | Issue | Implement crucial privacy, personalization, and notification settings to optimize the user’s experience as much as possible, making sure they have access to enabling/disabling a variety of features whenever they desire. | 28 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/28 | Backlog
modestmag-dev | Issue | Create an automated notification system that is able to send over notifications of certain types to users based on their specified preferences in that field. | 29 | OPEN | drew-csci/opportunity_app_srping_2026 | modestmag-dev |  |  |  | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/29 | Backlog
nakiwem | Issue | Create and manage volunteer profile with experience history | 41 | OPEN | drew-csci/opportunity_app_srping_2026 | nakiwem | High Priority |  | As a volunteer (student), I want to create and manage my profile with my experience history so that organizations can view my past volunteer experience and skills so that I can be matched with suitable volunteer opportunities. Acceptance Criteria: Volunteer profile saves required information (name, email, phone) Allows add/edit/delete of experience entries and associated volunteer organizations Displays profile information after saving Saves profile information after logging out Implementation Tasks: Build/Design student profile UI w/ a personal info (name, email, phone) and experience section Implement add/edit/delete functionality for profile Build/Design profile summary view page Wireframe: Student Profile (Public View) - (Wireframe 6) Story Points: 5 | 0 |  |  |  | 2026-03-02 | 2026-03-04 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/41 | In Progress
nakiwem | Issue | Create and manage organization profile with impact metrics | 40 | OPEN | drew-csci/opportunity_app_srping_2026 | nakiwem | High Priority |  | As an organization, I want to create and manage our organization’s profile with impact metrics so that student volunteers can understand our mission and the difference/change we want to make. Acceptance Criteria: Organization profile saves required information (name, mission, location, contact info) Allows add/edit/delete of impact metrics Saves profile information after logging out Displays profile information after saving Implementation Tasks: Build/Design organization profile UI (name, mission, location, contact info) Implement add/edit/delete functionality for profile Connect impact metrics and organization profile to database Wireframe: Organization Profile (Public View) - (Wireframe 5) Story Points: 5 | 0 |  |  |  | 2026-03-02 | 2026-03-04 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/40 | Backlog
nakiwem | Issue | Create apply to opportunity and track application status page | 42 | OPEN | drew-csci/opportunity_app_srping_2026 | nakiwem | High Priority |  | As a volunteer, I want to be able to apply for opportunities and track the application status so that I know whether I have been accepted, denied, or am still under review. Acceptance Criteria: Allows volunteer to fill out and submit an application for an opportunity Prevents volunteer from sending out duplication applications to organization Volunteer receives a message when their application has been submitted Displays application status (accepted, denied, or still under review) Updates application status when organization has made a decision Volunteer should be able to save their application process and go back later to complete Implementation Tasks: Build/Design application submission form and apply button Implement backend logic to save and store submissions Prevent duplication applications to be submitted for same opportunity Build/Design application tracking view for student volunteer Wireframe: Volunteer Profile (Public View) - (Wireframe 6) & Opportunity Search & Browse (Wireframe 3) Story Points: 5 | 0 |  |  |  | 2026-03-02 | 2026-03-04 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/42 | Backlog
NguyenTin2026 | Issue | US-009 – View peer activity feed of recent experiences | 3 | OPEN | drew-csci/opportunity_app_srping_2026 | NguyenTin2026 | Medium Priority |  | As a volunteer, I want to view a peer activity feed of recent experiences so that I can see what other volunteers have done and learn from their experiences. Acceptance Criteria: The volunteer can access the activity feed from the dashboard or social section The system displays recent volunteer experiences from other users Each activity shows volunteer name, organization, and experience title The volunteer can scroll through the activity feed If there are no activities, the system displays a message "No recent activity available" Tasks: Build/Design activity feed UI page Connect activity feed to database to retrieve experiences Display activity information in chronological order Ensure the page loads properly and allows scrolling Wireframe Mapping: Student Home Dashboard – Social Feed section | 0 |  |  |  | 2026-02-25 | 2026-03-04 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/3 | Backlog
NguyenTin2026 | Issue | US-011 – Send messages to organizations with AI-assisted FAQ responses | 5 | OPEN | drew-csci/opportunity_app_srping_2026 | NguyenTin2026 | Medium Priority |  | As a volunteer, I want to send messages to organizations with AI-assisted FAQ responses so that I can quickly get answers to my questions. Acceptance Criteria: The volunteer can open the messaging section The volunteer can select an organization to message The volunteer can type and send messages The system provides AI-assisted FAQ suggestions The organization receives the message The volunteer can see sent messages in the chat Tasks: Build/Design messaging UI interface Implement message sending functionality Connect messaging system to database Integrate AI-assisted FAQ response feature Ensure messages are stored and displayed properly Wireframe Mapping: Messaging section – Student Dashboard | 0 |  |  |  | 2026-02-25 | 2026-03-04 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/5 | Backlog
pwei454 | Issue | US-007 Review and manage incoming volunteer applications | 17 | OPEN | drew-csci/opportunity_app_srping_2026 | pwei454 | High Priority |  | As an organization user, I want to review and manage incoming volunteer applications so that I can efficiently select qualified students and manage active volunteers. Priority: High Story Points: 5 Acceptance Criteria: 1. The organization can view a list of incoming applications grouped by opportunity. 2. Each application displays: - Student name - Opportunity title - Date applied - Current status 3. The organization can click “View Profile” to see the student’s profile and experience history. 4. The organization can select “Accept” or “Decline.” 5. When an organization selects “Accept,” status updates to “Accepted.” 6. When an organization selects “Decline,” status updates to “Declined.” 7. Volunteers receive a notification when status changes. 8. Accepted students appear in the “Current Volunteers” list. 9. Status changes persist after page refresh. Implementation Tasks: 1. Build the “Review Volunteers” list view for organizations. 2. Implement backend logic to retrieve applications grouped by opportunity. 3. Add Accept and Decline button functionality. 4. Implement notification trigger when application status changes. Wireframe Mapping: Organization Home Dashboard (Wireframe 4) | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/17 | In Progress
pwei454 | Issue | US-008 - Send Application Reminder to Organization | 18 | OPEN | drew-csci/opportunity_app_srping_2026 | pwei454 | Medium Priority |  | US-008 - Send Application Reminder to Organization As a volunteer, I want to send a reminder for my pending application so that the organization may review my application sooner. Priority: Medium Story Points: 3 Acceptance Criteria: 1. The reminder button appears only when application status is "Applied." 2. Volunteers can click "Remind About Me." 3. When the volunteer clicks "Remind About Me," a notification is sent to the organization. 4. The reminder option is not available if application status changes to "Accepted" or "Declined." Implementation Tasks: 1. Add the "Remind About Me" button to pending applications. 2. Implement a backend notification trigger for reminders. 3. Ensure the reminder option disappears when status changes. Wireframe Mapping: Student Home Dashboard – Your Applications (Wireframe 2) | 0 |  |  |  | 2026-03-01 | 2026-03-01 | https://github.com/drew-csci/opportunity_app_srping_2026/issues/18 | Backlog